## Slide 1
Schindler Weekly Status Report
31st July 2023

## Slide 2
The goal of the project is to deploy the Atlassian application on the AKS platform. The existing structure is like an application deployed on Azure VMs.
Applications should be deployed on AKS environments due to cost savings as well as security.
Applications will be available via applications gateway and WAF
3 Applications are already deployed on aks platform
1 application is deployed on azure vm
Schindler – AKS(Azure Kubernetes Service )
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 3
Scope: Application Deployment on the AKS platform
Deploy the application of Atlassian on the AKS cluster
Created services of AKS like storage account PVC , PostgreSQL database
Applications deployment on the DEV environment
UAT and PROD deployment and Support
Scope & Timelines
S No | Task | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Progress
1 | Atlassian app – Dev deployment | 6-June-2023 | 20-OCT-2023 | 8-May-2023 | TBD | TBD | 30%
2 | Atlassian app – JSM DEV deployment and testing | 1-May-2023 | 30-May-2023 | 14-May-2023 | 06-June-2023 | Completed | 100%
3 | Atlassian app – Jira DEV deployment, Data migration and testing ,Confluenece Dev | 25-June-2023 | 15-July-2023 | 25-June-2023 | 28-July-2023 | completed | 100%
4 | Sonarqube application Deployment, | 24-july-2023 | 1-Aug-2023 | 24-july-2023 | 8-Aug-2023 | In progress | 80%
4 | UAT & Prod Release | TBD | TBD | TBD |  | Yet to start | 0%
Timelines
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 4
Accomplishments & Key Callouts for Current Week
Accomplishments
Key Callouts
Application deployed to DEV environment.
Configuration setup
Configuration setup completed
Need to check end to end testing
AKS cluster– Completed
Helm Charts– Completed
Deployment of one of applications- Completed
Installation of VM and database non-aks platform
Data migration from Azure VM to AKS cluster for
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 5
Activities Planned Next Week / Next Steps
Activities Planned Next Week (31st July to 4th Aug)
AKS application deployment using helm chart
Integrations
Configuration of applications like database certificates adding, Proxy settings,
Created an application and infrastructure, database for a non-AKS platform on azure cloud using Terraform.
Configuring Windows VM for the workaround of SSH connection issue
Next Steps
Application configuration as per end-user requirement
Need to check database configuration-related settings on the application
Need to check end-to-end testing
After data migration need to check the configuration files
Plan is to install Prometheus and Grafana on aks cluster and configure the applications alerts
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 6
Risk/Issues
  These are the high-level issues that I faced there were some less critical issues also that I don’t want to highlight here.
  No risk as of now which needs to be added here but in the future that may come.
Issues | Status | Owner to resolve | Planned date
Faced issues for data migration from Vm to aks | In progress | Sandhya,Gianpiero,Networking team | 20 July to 30 July 2023

## Slide 7: Thank you