## Slide 1
Schindler Weekly Status Report
27th oct 2023

## Slide 2
The goal of the project is to deploy the Atlassian application on the AKS platform. The existing structure is like an application deployed on Azure VMs.
Applications should be deployed on AKS environments due to cost savings as well as security.
Applications will be available via applications gateway and WAF
3 Applications are already deployed on aks platform
4 applications are deployed on azure VM dev,QA
3 applications are live in production
Schindler – AKS(Azure Kubernetes Service )
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 3
Scope: Application Deployment on the AKS platform
Deploy the application of Atlassian on the AKS cluster
Created services of AKS like storage account PVC , PostgreSQL database
Applications deployment on the DEV,QA environment
UAT ,QA,and PROD deployment and Support
Scope & Timelines
S No | Task | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Progress
1 | Atlassian app – Dev,QA,Prod deployment | 6-June-2023 | 20-OCT-2023 | 8-May-2023 | TBD | TBD | 30%
2 | Atlassian app –Confluence,JSM,Jira,Sonarqube deployment and testing | 1-May-2023 | 30-May-2023 | 14-May-2023 | 06-June-2023 | Completed | 100%
3 | Atlassian app – Jira QA deployment, Data migration and testing | 19-Aug-2023 | 28-aug-2023 | 19-Aug-2023 | 28-aug-2023 | completed | 60%
4 | Production deployment started(Confluence,sonar,jsm) | 10-sep-2023 | 15-Sep-2023 | 15-Sep-2023 | 31-Oct-2023 | completed | 80%
4 | UAT & Prod Release | 15-Sep-2023 | TBD | 15-sep-23 |  | Yet to start | 50%
Timelines
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 4
Accomplishments & Key Callouts for Current Week
Accomplishments
Key Callouts
Application deployed to DEV and QA environment.
Application configuration
Configuration setup
Configuration setup completed
Data migration from azure vm to aks pvc volume
End-to-end testing is there for deployed applications.
Created confluence pages for AKS configuration , postgres database, and application configuration
AKS cluster– Completed
Helm Charts– Completed
Deployment of one of applications- Completed
Installation of VM and database non-aks platform
Data migration from Azure VM to AKS cluster for
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 5
Activities Planned Next Week / Next Steps
Activities Planned Next Week (21st Sep to 29th Sep)
AKS application deployment using helm chart
Integrations
Configuration of applications like database certificates adding, Proxy settings,
Created an application and infrastructure, database for a non-AKS platform on azure cloud using terraform.
Configuring Windows VM for the workaround of SSH connection issue
Next Steps
Application configuration as per end-user requirement
Need to check database configuration-related settings on the application
Need to check end-to-end testing
After data migration need to check the configuration files
Plan is to install Prometheus and Grafana on aks cluster and configure the applications alerts
To deploy application QA environment
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 6
Risk/Issues
  These are the high-level issues that I faced there were some less critical issues also that I don’t want to highlight here.
  No risk as of now which needs to be added here but in the future that may come.
Issues | Status | Owner to resolve | Planned date
Faced issues for Clustering and reindexing | In Progress | Sandhya,Gianpiero | 15 Sep to 22 Sep 2023

## Slide 7: Thank you