## Slide 1
Schindler Weekly Status Report
9th June 2023

## Slide 2
The goal of the project is to deploy the Atlassian application on the AKS platform. The existing structure is like an application deployed on Azure VMs.
Applications should be deployed on AKS environments due to cost savings as well as security.
Applications will be available via applications gateway and WAF
Schindler – AKS(Azure Kubernetes Service )
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 3
Scope: Application Deployment on the AKS platform
Deploy the application of Atlassian on the AKS cluster
Created services of AKS like storage account PVC , PostgreSQL database
Applications deployment on the DEV environment
UAT and PROD deployment and Support
Scope & Timelines
S No | Task | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Progress
1 | Requirements & Design | 08-May-2023 | 12-May-2023 | 8-May-2023 | 12-May-2023 | Completed | 100%
2 | Atlassian app – Dev deployment | 14-May-2023 | 30-May-2023 | 14-May-2023 | 06-June-2023 | Completed | 100%
3 | Atlassian app – Dev testing | 06-June-2023 | 16-June-2023 | 06-June-2023 |  | In Progress | 70%
4 | UAT & Prod Release | TBD | TBD | TBD | TBD | Yet to start | 0%
Timelines
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 4
Accomplishments & Key Callouts for Current Week
Accomplishments
Key Callouts
Application deployed to DEV environment.
Configuration setup
AKS cluster– Completed
Helm Charts– Completed
Deployment of one of application- Completed
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 5
Activities Planned Next Week / Next Steps
Activities Planned Next Week (12th June to 16th June)
AKS application deployment using helm chart
Integrations
Configuration of applications like database certificates adding, Proxy settings,
Creating an application and infrastructure, database for a non-AKS platform on azure cloud using Terraform.
Configuring windows VM for the workaround of SSH connection issue
Next Steps
Application configuration as per end-user requirement
Need to check database configuration-related settings on the application
Notes: Source: Investor Presentation 2021, Annual Report 2021

## Slide 6
Risk/Issues
  These are the high-level issues that I faced there were some less critical issues also that I don’t want to highlight here.
  No risk as of now which needs to be added here but in the future that may come.
Issues | Status | Owner to resolve | Planned date
Facing issues on Terraform, and docker locally because of some authentication. | In progress | Sandhya, Gianpiero | 12-June to 16-June-23
Facing issues with connecting VM using SSH due to firewall rules. | In progress | Network team of Schindler | 12-June to 16-June-23

## Slide 7: Thank you